## Taulukko1
		Days to complete	Time estimate [h]	Weekly time [h]
Week 1	04.04.16
Setting up team		1	0,1
Sprint backlog		7	0,5
UML diagram		14	0,5
Example code		7	0,5	1,6

Week 2	11.04.16
Final UML model			0,5
Work on code prototype		14	0,5
Starting unit tests		21	0,5
Working examples of QR codes		14	0,5
directions from reception		7	0,5
Update gantt chart		21	0,5	3

Week 3	18.04.16
Work on code prototype			0,5
Unit tests			0,5
Examples of QR codes			0,5
Update gantt chart			0,5	2

Week 4	25.04.16
Unit tests			0,5
Add extra features		7	0,5
Perform dry run of demo		7	0,5
Update gantt chart			0,5	2

Week 5	02.05.16
Ensure all deliverables are submited		7	0,5
Commit project to github		7	0,5
Demo project in lab time			0,5	1,5

	Total time [h] =	10,1

Setting up team	04.04.16	1
Sprint backlog	04.04.16	7
UML diagram	04.04.16	14
Example code	04.04.16	7

Work on code prototype	11.04.16	14
Starting unit tests	11.04.16	21
Working examples of QR codes	11.04.16	14
directions from reception	11.04.16	7
Update gantt chart	11.04.16	21

Add extra features	25.04.16	7
Perform dry run of demo	25.04.16	7

Ensure all deliverables are submited	02.05.16	7
Commit project to github	02.05.16	7